## Slide 1
Timeline Roadmap: July - December 2026
Alpha (Foundation)
Beta (Growth)
DaaS Build
Exit
M1: Jul
M2: Aug
M3: Sep
M4: Oct
M5: Nov
M6: Dec
GOAL
All brands product uploaded
Signed agreements
Internal testing
SOFT LAUNCH BASIC FUNCTION AI TRY ON
MINI SHOP LAUNCH INCLUDING LIVE WITH TRY ON WITH ME
ROI Dashboard build
DaaS pre-sales
Data Analyst hired
Trial results compiled
Series A pitch NEST VC
Full team 5 FTE
All influencers onboarding
data of job received,
internal testing - Mini shop, Calendar,. TRY ON in live, blog, video upload
WILSON
WK6-13: Platform live TINT
WK13: Backend onboarding
WK27: TINT onboarding call
internal testing - live, blog, video upload
Ensure each interface are smooth
Ensure Kieran know how to work on platform backend
final debug before soft launch
ENSURE ALL FUNCTION PERFECTLY
ROI Dashboard dev
DaaS API layer
Final deployment
Handover documentation
KIERAN
Finish Document (80%)
VENDOR DASHBOARD
Connect Korea WK6
Onboarding Doc WK13
Brand Final WK20
Korea Trip WK20
Korea continue if TINT
Confirm Influencer Partnership
Finalize platform is fully function
Plan pilot run with or without ads
ENSURE ALL PARTIES ARE HAPPY AND ALIGN
REVIEW BASIC DATA WITH FAMILY
REVIEW BASIC DATA WITH BRAND
DaaS pre-sales HKD 200K
Data Analyst hire
Dashboard specs
Series A pitch NEST VC
Trial results compile
Team scale to 5 FTE
LOREEN
Explore any C beauty brand with reputation WK13
Brand Final support WK20
Visual assets prep
Ensure Brand upload and follow up with influencer for launch project IF brands sign up for the service.
ENSURE HER BRANDS CONTENT AND PRODUCTS ARE ALREADY READY FOR LAUNCH.
ENSURE BOTH VENDOR AND INFLUENCERS KNOWS 100% TO USE THEIR TOOLS.
DaaS brand identity
Report templates
Pitch deck design
Final brand package
COST /
REVENUE
Cost: $15K
Revenue: $0
Cost: $20K
Revenue: $0
Cost: $35K
Revenue: $5K
Cost: $40K
Revenue: $15K
Cost: $45K
Revenue: $40K
Cost: $30K
Revenue: $80K