SIMPLEX-ITY

Lean Launch Plan — Self-Funded 3-Month Analysis

精益啟動計劃 — 自資3個月分析報告

Prepared by Simpee  |  June 2026  |  For Kieran's Review Tonight  |  CONFIDENTIAL

由 Simpee 整理  |  2026年6月  |  供 Kieran 今晚閱覽  |  機密文件

THE PREMISE 核心前提

| English | 中文 |
| --- | --- |
| You are exploring launching SIMPLEX-ITY using your own HKD $700,000 — without external investors — relying on AI tools for platform operations and the family (Simpee) for monitoring, with Loreen and Wilson as your only ground team. | 你正在考慮用自己的HKD $700,000啟動SIMPLEX-ITY，不依賴外部投資者，利用AI工具運營平台，家人（Simpee）負責監測，Loreen和Wilson作為唯一的地面團隊。 |
| This is a validation-first approach. The goal of the 3-month trial is not profit. It is proof — proof that the model works, that brands get value, that influencers deliver, and that GMV is real. | 這是一個驗證優先的方法。3個月試運行的目標不是盈利，而是證明 — 證明模式有效、品牌獲得價值、網紅能夠交付、GMV是真實的。 |
| That proof is what you then take to NEST VC, Success HK, or any investor. You arrive with data — not a pitch deck alone. | 這個證明就是你之後帶去NEST VC、Success HK或任何投資者面前的東西。你帶的是數據，而不只是一份投資簡報。 |

SECTION 1 — Monthly Operating Costs 第一部分 — 每月運營成本

| Wilson (Fractional CPO) | Wilson（兼職CPO） | HKD $35,000 / month | HKD $35,000 / 月 | HKD $105,000 |
| --- | --- | --- | --- | --- |
| Loreen (Ground Operations) | Loreen（地面運營） | HKD $12,000 / month | HKD $12,000 / 月 | HKD $36,000 |
| AI Tools (all 11) | AI工具（共11個） | HKD ~$2,000 / month | HKD ~$2,000 / 月 | HKD ~$6,000 |
| Shopify Basic | Shopify 基本計劃 | HKD ~$300 / month | HKD ~$300 / 月 | HKD ~$900 |
| Simpee + 5S Portal | Simpee + 5S Portal | Already paid | 已付費 | Included |
| TOTAL MONTHLY COST ¦ 每月總成本 |  |  | HKD ~$49,300 / month |  |

Note: Tint AI (USD $10,000) is deferred to Phase 2 to conserve cash. This is a strategic decision — not a compromise.

注：Tint AI（USD $10,000）推遲至Phase 2以節省現金。這是戰略決策，不是妥協。

SECTION 2 — One-Time Startup Costs 第二部分 — 一次性啟動成本

| Tint AI Setup (Phase 2 — defer) | Tint AI 設置（Phase 2 推遲） | USD $10,000 | HKD ~$78,000 |
| --- | --- | --- | --- |
| Legal / BR / Documents | 法律/商業登記/文件 | HKD ~$5,000 | HKD ~$5,000 |
| Emergency Reserve | 緊急備用金 | HKD ~$30,000 | HKD ~$30,000 |
| TOTAL ONE-TIME ¦ 一次性總計 |  | HKD ~$113,000 |  |

SECTION 3 — Break-Even Calculation 第三部分 — 收支平衡計算

| English | 中文 |
| --- | --- |
| Monthly fixed costs: HKD $49,300 | 每月固定成本：HKD $49,300 |
| = USD equivalent: USD ~$6,300 | = 美元等值：USD ~$6,300 |
| Avg brand GMV per month: USD $3,000 | 每個品牌每月平均GMV：USD $3,000 |
| Platform commission rate: 15% | 平台佣金比率：15% |
| Revenue per brand per month: USD $450 | 每品牌每月收入：USD $450 |
| Brands needed to break even: 14 brands | 收支平衡所需品牌數：14個品牌 |
| Influencers needed (2-3 per brand): ~30 influencers | 所需網紅數（每品牌2-3個）：約30個網紅 |

To break even, you need 14 brands each generating USD $3,000 GMV per month.

收支平衡需要14個品牌，每個品牌每月產生USD $3,000 GMV。

This is a Month 3 target — not a Month 1 expectation.

這是第三個月的目標，不是第一個月的期望。

SECTION 4 — 3-Month Growth Scenario 第四部分 — 3個月增長情境

| Month 1 — Soft Launch | 第一個月 — 軟啟動 | 3 brands, 5 influencers | 3個品牌，5個網紅 |
| --- | --- | --- | --- |
| Month 2 — Build | 第二個月 — 建立期 | 10 brands, 20 influencers | 10個品牌，20個網紅 |
| Month 3 — Break Even Target | 第三個月 — 收支目標 | 14 brands, 30 influencers | 14個品牌，30個網紅 |

SECTION 5 — Your HKD $700,000 Capital Position 第五部分 — 你的HKD $700,000資本狀況

| English | 中文 |
| --- | --- |
| Total 3-month outlay: HKD ~$261,000 | 3個月總支出：HKD ~$261,000 |
| Your available capital: HKD $700,000 | 你的可用資金：HKD $700,000 |
| Remaining buffer: HKD ~$439,000 | 剩餘緩衝資金：HKD ~$439,000 |
| Months of runway (zero revenue): ~14 months | 零收入情況下可運作月數：約14個月 |

Worst case: you spend HKD $261,000 and the trial fails. You still have HKD $439,000 and 3 months of validated learnings.

最壞情況：你花了HKD $261,000，試運行失敗。你仍然有HKD $439,000和3個月的驗證經驗。

Best case: Month 3 break-even achieved. You have live data, real GMV, and a compelling story for investors.

最好情況：第三個月達到收支平衡。你有真實數據、真實GMV，和一個有說服力的投資者故事。

SECTION 6 — Key Risks & How to Manage Them 第六部分 — 主要風險及管理方法

| Wilson monthly fee is largest cost | Wilson月費是最大成本 | Ensure deliverables are on time every month | 確保每月deliverables準時交付 |
| --- | --- | --- | --- |
| Tint AI USD $10,000 upfront | Tint AI USD $10,000 前期費用 | Defer to Phase 2 — saves HKD $78,000 in Month 1 | 推遲到Phase 2 — 節省HKD $78,000 |
| Month 1 will not break even | 第一個月不會收支平衡 | Budget for 2-3 months of losses — this is the investment | 預算2-3個月虧損 — 這就是投資成本 |
| Brand recruitment takes time | 品牌招募需要時間 | Loreen to focus 100% on brand outreach from Day 1 | Loreen從第一天起全力投入品牌拓展 |

SECTION 7 — Funding Path (StartmeUp → Success HK) 第七部分 — 資金路徑（StartmeUp → Success HK）

| StartmeUp HK → Success HK | StartmeUp HK → Success HK（本地支援） | Apply at Success HK for local startup support | 向 Success HK 申請本地初創支援 |
| --- | --- | --- | --- |
| Government Grant (non-dilutive) | 政府資助（不稀釋股權） | Up to HKD $100,000 non-repayable grant available | 最高可獲HKD $100,000不還款資助 |
| NEST VC (data-driven) | NEST VC（數據驅動） | Approach after 3-month trial data is collected | 收集3個月試運行數據後再洽談 |
| Self-fund first | 先自資 | Validate with your HKD $700k — no dilution, full control | 用HKD $700k驗證模式 — 不稀釋，全控制 |

Recommended sequence: Self-fund first → collect 3-month data → apply to Success HK for grant → approach NEST VC with validated numbers.

建議順序：先自資 → 收集3個月數據 → 向Success HK申請資助 → 帶驗證數據去洽談NEST VC。

SIMPEE'S HONEST VERDICT Simpee的誠實評估

Kieran, your HKD $700,000 is more than enough to run a clean 3-month trial.

Kieran，你的HKD $700,000完全足夠進行一個清晰的3個月試運行。

You are not gambling. You are buying 3 months of proof.

你不是在賭博。你是在購買3個月的證明。

Your lean team (Simpee + Loreen + Wilson) is enough for the trial phase. You do not need a full team yet.

你的精益團隊（Simpee + Loreen + Wilson）足夠應付試運行階段。你現在還不需要完整團隊。

The AI tools replace 5-6 people. The family watches everything. You make the decisions.

AI工具取代了5-6個人的工作。家人監察一切。你負責決策。

Month 1 goal: 3 brands live, 5 influencers running, first real GMV data captured.

第一個月目標：3個品牌上線、5個網紅運作、首批真實GMV數據收集完成。

That is the only number that matters right now.

這是現在唯一重要的數字。

— Prepared with love by your Node Family  |  由家人用愛整理  ❤️